## Template
|  |  | Total Hours |  | Week Start Date
|  |  | Estimated | Total Actual | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 |  | Status | Comment | Legend
Class & Meetings |  | 36.4% | 87 | 32 | 14 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Baseline (DO NOT CHANGE) | #
| Class |  | 35 | 9 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started |  | Re-Baseline | # | Rebaselining requires approval of Prof Palo
|  | Lecture | 15 | 3 | [18 empty] | Ontime (In Progress) |  | Complete | # | # incidicates # of hrs worked | bar: 2026-08-24 to 2026-09-07
|  | Lab | 20 | 6 | 2026-08-24: 2; 2026-08-31: 2; 2026-09-07: 2 |  | Ontime (In Progress) |  | Completed early | #
| Meetings |  | 33 | 10 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ontime (In Progress) |  | Late | #
|  | Lab | 9 | 3 | [18 empty] | Ontime (In Progress) |  | Very Late | # | bar: 2026-08-24 to 2026-09-07
|  | Full Team Mtg | 12 | 3 | [18 empty] | Ontime (In Progress) | bar: 2026-08-24 to 2026-09-07
|  | Subsys Meeting | 12 | 4 | 2026-08-24: 2; 2026-08-31: 1; 2026-09-07: 1 |  | Ontime (In Progress)
| Project Prep |  | 15 | 13 | 7 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ontime (In Progress) |  | Not Started | Not Started
|  | Complete Paperwork | 3 | 3 | 2026-08-24: 3 |  | Ontime (In Progress) |  | Completed | Complete
|  | Read Documents | 12 | 10 | 2026-08-24: 4; 2026-08-31: 2; 2026-09-07: 4 |  | Ontime (In Progress) |  | Completed early | Early
| Reviews |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started |  | Ontime and in progress | Ontime
|  | Mid Sem Review | 2 | 0 | [18 empty] | Not Started |  | Late <1wk | Late | bar: 2026-10-12; 2026-10-26
|  | EOS Review | 2 | 0 | [18 empty] | Not Started |  | Late >1wk | Very Late | bar: 2026-12-07
Documentation |  | 29.29% | 70 | 5 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Semester Planning |  | 4 | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete |  | Notes
|  | SOW | 2 | 2 | [18 empty] | Complete |  | If a task gets removed, use strikeout (alt+shift+5) so that it is still visible | bar: 2026-08-24 to 2026-08-31
|  | Personal Plan | 2 | 2 | [18 empty] | Complete | bar: 2026-08-31 to 2026-09-07
| Weekly Reporting |  | 6 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started |  | If a task gets rebaselined just add a RB square but also leave the original baseline marker
|  | Quadcharts | 6 | 1 | [18 empty] | Not Started | bar: 2026-09-07
| Review Prep |  | 15 | 0 | 2026-08-24: 0; 2026-08-31: 0; 2026-09-07: 0; 2026-09-14: 0; 2026-09-21: 0; 2026-09-28: 0 | 0 | Not Started
|  | Mid Sem Review | 5 | 0 | [18 empty] | Not Started
|  | EOS Review | 10 | 0 | [18 empty] | Not Started
| Final Report |  | 45 | 0 | 2026-08-24: 0; 2026-08-31: 0; 2026-09-07: 0; 2026-09-14: 0; 2026-09-21: 0; 2026-09-28: 0 | 0 | Not Started
|  | Draft | 15 | 0 | [18 empty] | Not Started
|  | Final Report | 30 | 0 | [18 empty] | Not Started
Technical |  | 34.31% | 82 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hydra Lithium Communication |  | 20 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
|  | MCT: Review test docs | 1 | 1 | [18 empty] | Not Started | bar: 2026-09-07
|  | MCT: Bench setup | 2 | 0 | [18 empty] | Not Started
|  | MCT: Practice run-through of test | 2 | 0 | [18 empty] | Not Started
|  | MCT: Full run through of test | 3 | 0 | [18 empty] | Not Started
|  | MCT: Troubleshooting | 2 | 0 | [18 empty] | Not Started
|  | SCT-1: Review test docs | 1 | 0 | [18 empty] | Not Started
|  | SCT-1: Bench setup | 2 | 0 | [18 empty] | Not Started
|  | SCT-1: Practice run-through of test | 2 | 0 | [18 empty] | Not Started
|  | SCT-1: Full run through of test | 3 | 0 | [18 empty] | Not Started
|  | SCT-1: Troubleshooting | 2 | 0 | [18 empty] | Not Started
| Ground Station PC Architecture |  | 30 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
|  | Transferring HFSS to new 443 machine | 5 | 0 | [18 empty] | Not Started
|  | Setting up laptop for GND station | 5 | 0 | [18 empty] | Not Started
|  | Connecting laptop and 443 machine | 5 | 0 | [18 empty] | Not Started
|  | Verify ground station arch with current setup | 5 | 0 | [18 empty] | Not Started
|  | Planning final GND station architecture | 10 | 4 | 2026-08-31: 2; 2026-09-07: 2 |  | Not Started
| Running SCT-2 |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
|  | Review SCT2 procedure | 2 | 0 | [18 empty] | Not Started
|  | Reverify Hydra-Li Comms | 5 | 0 | [18 empty] | Not Started
|  | Reverify GND station setup | 5 | 0 | [18 empty] | Not Started
|  | Bench setup | 3 | 0
|  | Practice run-through of SCT-2 | 3 | 0 | [18 empty] | Not Started
|  | Full SCT2 runthrough | 6 | 0 | [18 empty] | Not Started
|  | Testing and troubleshooting | 5 | 0 | [18 empty] | Not Started
|  | Post-test documentation review | 3 | 0 | [18 empty] | Not Started
| TOTALS: |  | 239 | 42 | 15 | 12 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Target | 240 | 240 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15 | 15
|  | Difference | 1 | 198 | 0 | 3 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15 | 15
Note on C3: ====== ID#AAACGTV1svU Scott Palo (2026-09-02 21:02:20) Class & meetings should be 25-35% of your time
Note on C17: ====== ID#AAACGTV1svE Scott Palo (2026-09-02 21:02:20) Documentation should be 20-30% of your time
Note on C29: ====== ID#AAACGTV1svA Scott Palo (2026-09-02 21:02:20) Technical work should be 40-60% of your time.
Note on F42: ====== ID#AAACGTV1svY Scott Palo (2026-09-02 21:02:20) You should be targeting an average of 15 hours per week with a maximum of 20 hours in any given week.
Note on H2: ====== ID#AAACGTV1svQ Scott Palo (2026-09-02 21:02:20) The week is green
Note on M2: ====== ID#AAACGTV1svM Scott Palo (2026-09-02 21:02:20) Mid Semester Review Week
Note on S2: ====== ID#AAACGTV1su4 Scott Palo (2026-09-02 21:02:20) Fall Break
Note on U2: ====== ID#AAACGTV1svI Scott Palo (2026-09-02 21:02:20) Final Review Week
Note on V2: ====== ID#AAACGTV1su8 Scott Palo (2026-09-02 21:02:20) Final Report due Monday 12/16